## Timeline
Compliance Readiness Audit | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01
Create 5th Year Review Committee | bar: 2018-11-01
Attend SACS ANNUAL Conference
Provide 2015 Reaffirmation Submission for Committee Review | bar: 2018-12-01
Create Institutional Progress Tracking Tool to Address 5th Year Readiness
Conduct Committee Orientation | bar: 2019-01-01
Review Principles of Accreditation
Review Standard Changes with Committee | bar: 2019-01-01
Create Working Groups
Review Previous 2015 Reaffirmation Submission with Each Sub Committee | bar: 2019-01-01 to 2019-02-01
Create an Initial Assessment of Each Standard and Gaps
Create Action Plan to Address Any Initially Identified Gaps | bar: 2019-03-01
Sub Groups Report Data Fall 2016 - Fall 2019
Sub Groups Provide Narrative for Compliance Standards Fall 2016 - Fall 2019 | bar: 2019-03-01 to 2019-05-01
Attend SACS Summer Institute
Readiness Audit Conducted to Address Any Gaps in Policy or Evidence Collection | bar: 2019-06-01
6 Month Action Plans Created for any Gaps Identified
Roundtable Discussion of Progress on Action Plans | bar: 2019-10-01
Attend SACS ANNUAL Conference
Compliance Certification Report
Narrative Revisions by Subcommittees | bar: 2019-12-01 to 2020-01-01
Report Edits
Review and Feedback of Report by Sacs Leadership Committee | bar: 2020-03-01 to 2020-04-01
Consultant Review/Feedback
Revision of Report based on Feedback | bar: 2020-04-01 to 2020-05-01
Final Review by Sacs Leadership Committee and Executive Team
Report Preparation and Submission | bar: 2020-07-01 to 2020-09-01